## Decision Register
Decision ID | Policy Area | Definitive Provisional Wording | Requester's Provisional Preference | Formal Approval Status | Required Approver Role | Actual Approver Name | Approval Date | Approval Evidence Reference | Outstanding Clarification | Technical Dependencies | Implementation Impact | Verification Requirements | Release-Gate Impact | Notes & Next Action
D01 | Buyer Return Window | A return request must be raised within 14 days of the sub-order delivery timestamp (deliveredAt + 14 days). This is Clock 1 — independent of the merchant response deadline. | Provisionally accepted by requester — formal business approval pending. | PROVISIONAL — PENDING APPROVAL | Head of Operations / COO (co: Customer Experience) | UNKNOWN | NOT PROVIDED | NOT PROVIDED | How does return eligibility interact with cancellations, partial deliveries, and exceptional cases (e.g. buyer never received)? | None — foundational window | Implemented in returns.service.ts (RETURN_WINDOW_DAYS constant). No code change if 14 days approved. | Unit test: window enforcement. Integration: return request rejected after 14 days. Edge cases: partial delivery, cancellation. | BLOCKED — business approval required. | Lock §5.2. Env-overridable via RETURN_WINDOW_DAYS. Next: approve 14-day value or specify alternative.
D02 | Merchant Response SLA | The merchant must respond to a return request within 72 hours of request creation. This is Clock 2 — independent of the buyer return-eligibility window. When the deadline passes, the request is escalated (not expired). | Provisionally accepted by requester — formal business approval pending. | PROVISIONAL — PENDING APPROVAL | Head of Merchant Partnerships | UNKNOWN | NOT PROVIDED | NOT PROVIDED | What is the authoritative event and timestamp that starts the 72-hour clock? (OQ-02) | D01 (eligibility window defines outer boundary) | Currently stored as return_requests.expires_at. Current code auto-expires (REQUESTED→EXPIRED). Requires FSM amendment + worker redesign if escalation approved. | Unit: 72h deadline enforcement. Integration: escalation triggered at deadline. Idempotency: no duplicate escalation. | BLOCKED — approval required. Material implementation change. | Lock §5.8. Column expires_at retained; semantic meaning changes. Next: confirm 72h + escalation.
D03 | Merchant Timeout Behavior | When the merchant response deadline passes without action, the request transitions REQUESTED → ESCALATED and remains open. No automatic approval, rejection, or expiry occurs solely because of the timeout. | Provisionally accepted by requester — formal business approval pending. | PROVISIONAL — PENDING APPROVAL | Head of Merchant Partnerships (co: Head of Operations) | UNKNOWN | NOT PROVIDED | NOT PROVIDED | None — provisional policy is clear. Requires FSM state ESCALATED + migration + worker redesign. | D02 (merchant response SLA), D11 (admin escalation SLA) | MATERIAL: Add ESCALATED state to FSM, update migration CHECK constraint, redesign worker to escalate (not expire), add admin escalated-queue UI. New outbox event return.escalated. | Unit: FSM 12+1 states. PostgreSQL: concurrent timeout processors → 1 escalation. Idempotency: re-processing safe. | BLOCKED — approval required. Critical-path item. | Conflict C-01 in reconciliation. Current: REQUESTED→EXPIRED. Proposed: REQUESTED→ESCALATED. Next: approve escalation.
D04 | Commission — Merchant-Responsible | Reverse the commission attributable to the NET VALUE OF GOODS REFUNDED for confirmed merchant-responsible returns. Formula: round(commission_total × (net_goods_returned / net_goods_total)). VAT-exclusive, delivery-fee-exclusive. Uses immutable checkout-time snapshots. | Provisionally accepted by requester — formal business approval pending. | PROVISIONAL — PENDING APPROVAL | Finance Lead / CFO | UNKNOWN | NOT PROVIDED | NOT PROVIDED | What is the approved deterministic allocation method when commission snapshots exist only at order level? (OQ-04 — CRITICAL BLOCKER) | D05, D06, D07 (consistent treatment). OQ-04 (allocation method). | MATERIAL: Refund calculation extension, settlement adjustment for commission reversal, new responsibility_category field. VAT-exclusive only. | Unit: formula for each category. PostgreSQL: settlement adjustment, cumulative cap. Financial: VAT-exclusive confirmed. | BLOCKED — approval + OQ-04 resolution required. | Conflict C-02. Formula CORRECTED in v3 — net goods only, not refund_amount/confirmed_payment. Next: Finance approve.
D05 | Commission — Buyer Remorse | Retain the original commission for buyer-remorse (CUSTOMER_REQUEST) returns. No commission reversal under any circumstance. | Provisionally accepted by requester — formal business approval pending. | PROVISIONAL — PENDING APPROVAL | Finance Lead / CFO | UNKNOWN | NOT PROVIDED | NOT PROVIDED | None — policy is clear. | D04, D06, D07 (consistent treatment) | Explicit branch in responsibility-dependent logic. No reversal for buyer-remorse. | Unit: no reversal for CUSTOMER_REQUEST. Integration: commission unchanged after buyer-remorse refund. | BLOCKED — approval required for consistency. | Constraint §5.3: buyer-remorse must not reverse commission. Next: Finance confirm.
D06 | Commission — Platform-Responsible | Reverse the commission attributable to the NET VALUE OF GOODS REFUNDED for confirmed platform-responsible returns. Same formula and constraints as D04. | Provisionally accepted by requester — formal business approval pending. | PROVISIONAL — PENDING APPROVAL | Finance Lead / CFO | UNKNOWN | NOT PROVIDED | NOT PROVIDED | None — resolved in provisional policy. | D04, D05, D07 | Same as D04 — responsibility-dependent commission reversal. | Same as D04 verification for platform-responsible category. | BLOCKED — approval required. | Previously UNRESOLVED, now resolved. Next: Finance approve.
D07 | Commission — Carrier Damage | Reverse the commission attributable to the NET VALUE OF GOODS REFUNDED for confirmed carrier-damage returns. Same formula and constraints as D04. Carrier recovery pursued separately (not implemented in P13). | Provisionally accepted by requester — formal business approval pending. | PROVISIONAL — PENDING APPROVAL | Finance Lead / CFO | UNKNOWN | NOT PROVIDED | NOT PROVIDED | None — resolved in provisional policy. | D04, D05, D06, D10 | Same as D04 — responsibility-dependent commission reversal. | Same as D04 verification for carrier-damage category. | BLOCKED — approval required. | Previously UNRESOLVED, now resolved. Carrier recovery NOT implemented. Next: Finance approve.
D08 | Delivery Fee — Full Sub-Order Baseline | The original delivery fee is refunded only for a full-sub-order return (all items, full quantity). Partial returns refund goods + proportional VAT only. Delivery fee is NOT refunded on partial returns under the baseline. | Provisionally accepted by requester — formal business approval pending. | PROVISIONAL — PENDING APPROVAL | Finance Lead (co: Head of Operations) | UNKNOWN | NOT PROVIDED | NOT PROVIDED | What is the delivery-fee allocation for mixed-item and partial-sub-order returns when an exception is approved? (OQ-05) | D09, D10 (exceptions) | Already implemented (AC-P13-006 verified 10/10). No code change if baseline approved. | Integration: full sub-order → delivery refunded. Partial → delivery NOT refunded. | BLOCKED — approval required. | Lock §7.3. Verified by browser E2E B03. Next: Finance approve baseline.
D09 | Delivery Fee — Admin Exception | Permit an administrator-authorized delivery-fee exception for confirmed merchant-responsible or platform-responsible partial returns, with reason recorded in audit trail. | Provisionally accepted by requester — formal business approval pending. | PROVISIONAL — PENDING APPROVAL | Finance Lead (co: Head of Operations) | UNKNOWN | NOT PROVIDED | NOT PROVIDED | What approval and audit evidence is required for delivery-fee exceptions? (OQ-06) | D08 (baseline), D03 (escalation path) | Admin UI override path, delivery-fee refund on partial, audit trail for exception reason. | Integration: admin-approved exception → delivery refunded on partial. Audit: reason recorded. | BLOCKED — approval required. | Conflict C-03. Next: Finance + Ops approve exception path.
D10 | Delivery Fee — Carrier Damage | For confirmed carrier damage: refund original delivery fee when damage materially compromises delivery of the order as a whole. Limited-impact partial cases → administrator review. Carrier recovery pursued separately (NOT implemented in P13). | Provisionally accepted by requester — formal business approval pending. | PROVISIONAL — PENDING APPROVAL | Finance Lead (co: Head of Operations) | UNKNOWN | NOT PROVIDED | NOT PROVIDED | Define "materially compromises delivery" vs "limited-impact partial" (OQ-11). Carrier recovery process (OQ-12 — not in P13 scope). | D07, D08, D09 | Carrier-damage classification, delivery-fee refund path, admin review for partials. Carrier recovery NOT implemented. | Integration: material impact → delivery refunded. Partial → admin review. Carrier recovery NOT tested. | BLOCKED — approval + OQ-11 required. | Previously UNRESOLVED, now resolved. Carrier recovery is separate workflow. Next: Finance define materiality.
D11 | Administrator Escalation SLA | Provisional administrator resolution target: 3 business days from escalation. Business calendar, timezone, holiday handling, and overdue-escalation process remain to be specified. | Provisionally accepted by requester — formal business approval pending. | PROVISIONAL — PENDING APPROVAL | Head of Operations / COO | UNKNOWN | NOT PROVIDED | NOT PROVIDED | Define business day, hours, timezone, weekends, holidays (OQ-01). Authoritative SLA start event (OQ-02). Overdue process. | D02, D03 (escalation must exist first) | Business-calendar config, SLA tracking, overdue-alert mechanism. | Integration: SLA countdown from escalation. Overdue detection after 3 business days. | BLOCKED — approval + OQ-01/OQ-02 required. | Previously UNRESOLVED, now resolved (3 business days). Calendar details TBD. Next: Ops define calendar.
D12 | Settlement Recovery | Recover settlement amounts through manual Finance/administrator adjustments. No automated clawback. Finalized order financial snapshots remain immutable. Post-finalization changes use auditable refund and settlement-adjustment records. | Provisionally accepted by requester — formal business approval pending. | PROVISIONAL — PENDING APPROVAL | Financial Controller | UNKNOWN | NOT PROVIDED | NOT PROVIDED | Finance reconciliation and authorization requirements for manual adjustments (OQ-07). | None — standalone financial process | Already implemented (AC-P13-013, AC-P13-014). No code change if approved. | Integration: PAID → new ADJUSTMENT. PENDING/CALCULATED → in-place update. Immutability: breakdown unchanged. | BLOCKED — approval required. | Lock §7.1. Constraint §5.5, §5.7. Next: Financial Controller approve.
D13 | Voucher Returns | Require administrator review for every voucher-related return. Voucher refunds are not auto-issued on merchant inspection alone. | Provisionally accepted by requester — formal business approval pending. | PROVISIONAL — PENDING APPROVAL | Finance Lead (co: Risk / Fraud) | UNKNOWN | NOT PROVIDED | NOT PROVIDED | Permitted outcomes after review and financial consequences (OQ-08). | None — standalone fraud control | Admin oversight partially implemented. May need explicit voucher-review workflow. | Integration: voucher return → admin review required. Authorization: admin-only. | BLOCKED — approval + OQ-08 required. | Lock §7.4. Constraint §5.6. Next: Finance + Risk approve + define outcomes.
D14 | Deployment Target | Target a limited single-process pilot, subject to all operational and release gates. Multi-instance production remains blocked until a durable or leader-coordinated scheduler is implemented, tested, and independently verified. | Provisionally accepted by requester — formal business approval pending. | PROVISIONAL — PENDING APPROVAL | CTO / Head of Engineering (co: Operations) | UNKNOWN | NOT PROVIDED | NOT PROVIDED | Pilot environment, scope, start criteria, success criteria (OQ-10). | D01–D13 (pilot scope depends on approved policies) | No code change for pilot selection. Multi-instance blocked. | Operational: exactly one worker-enabled instance confirmed. All 4 controls active. | BLOCKED — target must be explicitly selected. | Sign-off register §2. Constraint §5.8. Next: CTO select pilot.
D15 | Pilot Operational Controls | Single-process pilot with exactly one worker-enabled API instance and four operational controls: (1) alert on repeated polling errors, (2) monitor REQUESTED rows overdue >10 min, (3) designate one worker-enabled instance, (4) monitor startup and activity. | Provisionally accepted by requester — formal business approval pending. | PROVISIONAL — PENDING APPROVAL | CTO / Head of Engineering (co: Platform Ops / SRE) | UNKNOWN | NOT PROVIDED | NOT PROVIDED | Named operational owners, alert recipients, thresholds, rollback responsibility (OQ-09). | D14 (deployment target) | Operational runbook, alerting config, monitoring dashboards. No worker code change. | Operational: all 4 controls assigned, alerting tested, dashboards active, rollback plan documented. | BLOCKED — controls must be assigned and confirmed. | Sign-off register §2 Option A. Constraint §5.9. Next: Ops/SRE accept controls.

## Open Questions
Question ID | Category | Exact Answer Required | Accountable Role | Decision Needed | Dependent Decisions | What Remains Blocked | Impact if Unresolved | Priority | Status
OQ-01 | SLA Calendar | Define: business day, business hours, time zone, weekends, public holidays for the 3-business-day admin escalation target. | Head of Operations / COO | Approve calendar rules. | D11 | Admin SLA tracking implementation (WP-1F, WP-2F). | Cannot implement SLA tracking without calendar definition. | HIGH | OPEN
OQ-02 | SLA Triggers | What is the authoritative event and timestamp that starts each SLA clock (merchant 72h, admin 3-business-day)? | Head of Operations / COO | Confirm trigger events. | D02, D11 | SLA calculation implementation. | Incorrect trigger causes premature/delayed SLA measurement. | HIGH | OPEN
OQ-03 | Return Eligibility | How does the 14-day window interact with cancellations, partial deliveries, and exceptional cases? | Head of Operations / COO | Define eligibility rules for edge cases. | D01 | Edge-case implementation. | Ambiguous eligibility causes incorrect acceptance/rejection. | MEDIUM | OPEN
OQ-04 | Commission Allocation | What is the approved deterministic allocation method when commission snapshots exist only at order level? | Finance Lead / CFO | Approve proportional allocation by net goods value ratio, or specify alternative. | D04, D06, D07 | Commission reversal implementation (WP-1D, WP-2D). CRITICAL BLOCKER. | No deterministic commission reversal without this. Financial misstatement risk. | CRITICAL | OPEN
OQ-05 | Delivery-Fee Allocation | What is the delivery-fee allocation for mixed-item and partial-sub-order returns when an admin exception is approved? | Finance Lead (co: Ops) | Define: full delivery fee or proportional on exception? | D09, D10 | Delivery-fee exception implementation (WP-1E, WP-2E). | Ambiguous allocation causes incorrect refund amounts. | MEDIUM | OPEN
OQ-06 | Delivery-Fee Audit | What approval and audit evidence is required for delivery-fee exceptions? | Finance Lead (co: Risk) | Define: approver level, reason codes, audit trail. | D09 | Audit trail design for exceptions. | Exception approvals lack governance. | LOW | OPEN
OQ-07 | Settlement Authorization | What Finance reconciliation and authorization requirements apply to manual settlement adjustments? | Financial Controller | Define: authorization levels, reconciliation frequency, sign-off. | D12 | Finance governance process. | Manual adjustments lack financial governance. | MEDIUM | OPEN
OQ-08 | Voucher Outcomes | What are the permitted outcomes after admin review of a voucher return? Financial consequences of each? | Finance Lead (co: Risk) | Define: cash, voucher, store credit, reject + financial treatment. | D13 | Voucher review workflow implementation (WP-1G, WP-2G). | Admin reviewers have no policy guidance. | LOW | OPEN
OQ-09 | Pilot Owners | Who are the named operational owners, alert recipients, monitoring thresholds, and rollback responsibility? | CTO / Head of Engineering (co: SRE) | Name owners and configure alerts. | D15 | Pilot operational readiness (WP-3G). | Controls unowned and unenforced. | HIGH | OPEN
OQ-10 | Pilot Scope | What is the exact pilot environment, scope, start criteria, and success criteria? | CTO / Head of Engineering (co: Ops) | Define pilot parameters. | D14 | Pilot launch. | No measurable success/failure criteria. | HIGH | OPEN
OQ-11 | Carrier Materiality | What defines "materially compromises delivery" vs "limited-impact partial" for carrier-damage delivery-fee treatment? | Finance Lead (co: Ops) | Define materiality threshold. | D10 | Carrier-damage delivery-fee implementation. | Arbitrary delivery-fee decisions. | MEDIUM | OPEN
OQ-12 | Carrier Recovery | What is the carrier recovery process, evidence requirements, and timeline? | Head of Operations / COO | Define recovery workflow. NOTE: NOT in P13 scope. | D07, D10 | Separate workflow — does not block P13. | Ad hoc carrier recovery. | LOW (P14+) | OPEN — NOT IN P13

## Release Gates
Gate ID | Gate Name | Description | Status | Blocking Decisions | Blocking Questions | Evidence Available | Action Required
G-01 | Formal Business Approval | All 15 policy decisions (D01–D15) formally approved by designated approvers with attributable evidence. | BLOCKED | D01–D15 (all) | None — approval gate | 0 of 15 approved. No approver names, dates, or evidence. | Business owners approve each decision with name, role, date, rationale.
G-02 | Policy Ambiguity Resolution | All in-scope open questions resolved with definitive answers. | BLOCKED | D04, D06, D07, D09, D10, D11, D13 | OQ-01 through OQ-11 (OQ-12 out of P13 scope) | 12 open questions. 0 resolved. OQ-04 is CRITICAL. | Responsible roles provide definitive answers.
G-03 | Technical Implementation | FSM ESCALATED, commission reversal, delivery-fee exceptions, escalation worker, admin UI implemented. | BLOCKED | D03, D04, D06, D07, D09, D10, D11 | OQ-04, OQ-05, OQ-11 | Current code: auto-expire + uniform commission retention. Implementation not started. | Implement AFTER approval. Phase 2 work packages.
G-04 | Commission & Settlement Correctness | Commission reversal verified against immutable checkout-time snapshots. VAT-exclusive. Settlement adjustments verified. | BLOCKED | D04, D05, D06, D07, D12 | OQ-04 | Current tests: commission retention for all. Responsibility-dependent tests not written. | After implementation: integration tests for each category.
G-05 | Worker Scheduling & Deployment | Worker scheduling verified for selected deployment target. | BLOCKED | D14, D15 | OQ-09, OQ-10 | Worker registers on every replica. Pilot topology not confirmed. | After D14/D15: configure and verify pilot topology.
G-06 | Pilot Operational Readiness | All 4 operational controls assigned, alerting configured, dashboards active, rollback documented. | BLOCKED | D15 | OQ-09, OQ-10 | 0 of 4 controls assigned. | After D15: assign owners, configure, test.
G-07 | Deployment Target Sign-Off | Deployment target explicitly selected. | BLOCKED | D14 | OQ-10 | Not selected. | CTO explicitly selects target.
G-08 | Explicit Release Authorization | Authorized person grants explicit release authorization. | BLOCKED | G-01 through G-07 | All | Not granted. Gate: PASS WITH CONDITIONS — RELEASE AUTHORIZATION PENDING. | After all gates pass: authorized person grants release.
G-09 | Regression & Build Baseline | Full regression 3098/3098. P13 suites 162/162. Typecheck 9/9. Build 6/6. | PASS (pre-implementation) | None | None | Linux CI verified. Consistent with Windows. | Re-verify after implementation.
G-10 | P12 Regression Preservation | All P1–P12 tests continue to pass after P13 changes. | PASS (pre-implementation) | None | None | Full regression includes all P1–P12. 0 failures. | Re-verify after implementation.

## Approval Guide
Category | Decisions | Approver Role | Approval Sequence | Rationale | Dependencies | Open Questions
Return Window & Eligibility | D01 | Head of Operations / COO (co: Customer Experience) | 1st | Foundational window — all other return policies depend on a defined eligibility period. | None | OQ-03
Merchant Response & Escalation | D02, D03, D11 | Head of Merchant Partnerships (D02, D03) + Head of Operations (D11) | 2nd | Merchant SLA and timeout behavior are coupled. D11 defines admin resolution target. Must approve before FSM/worker implementation. | D01 | OQ-01, OQ-02
Commission Treatment | D04, D05, D06, D07 | Finance Lead / CFO | 3rd | All four form a single responsibility-dependent policy. Must approve as coherent set. | D02, D03 | OQ-04 (CRITICAL)
Delivery-Fee Treatment | D08, D09, D10 | Finance Lead (co: Head of Operations) | 3rd (parallel) | Baseline, exception, and carrier-damage form a coherent set. Parallel with commission. | D08 before D09/D10 | OQ-05, OQ-06, OQ-11
Settlement & Voucher Policy | D12, D13 | Financial Controller (D12) + Finance Lead / Risk (D13) | 4th | Operational financial policies. Independent of commission/delivery-fee. | None | OQ-07, OQ-08
Deployment & Operations | D14, D15 | CTO / Head of Engineering (co: Platform Ops / SRE) | 5th | Deployment target and operational controls after all policy decisions settled. | D01–D13 first | OQ-09, OQ-10
EXECUTIVE SUMMARY (v2 — corrected)
Contradictions corrected (v2):
C-01 | Commission formula corrected: net goods only (VAT-exclusive, delivery-fee-exclusive).
C-02 | Stale [UNRESOLVED] labels removed for platform/carrier commission.
C-03 | Stale [UNRESOLVED] label removed for carrier-damage delivery fee.
C-04 | Status terminology standardized: PROVISIONAL — PENDING APPROVAL used consistently.
C-05 | Commission allocation method (OQ-04) recorded as CRITICAL BLOCKER.
C-06 | expires_at semantics documented across current and proposed behavior.
Total decisions: | 15 (D01–D15)
Approved: | 0 of 15
Provisional — Pending Approval: | 15 of 15
Open questions: | 12 (OQ-01–OQ-12). OQ-04 is CRITICAL blocker.
Release gates: | 8 BLOCKED, 2 PASS (pre-implementation baseline)
Critical blockers:
1. | OQ-04 (commission allocation method) — Finance must approve before D04/D06/D07 implementation.
2. | OQ-01 (business calendar) — Ops must define before D11 implementation.
3. | All 15 formal approvals — no implementation authorized without approval.
Current gate: | PASS WITH CONDITIONS — RELEASE AUTHORIZATION PENDING
Technical verification: | COMPLETE — 3098/3098, 162/162, typecheck 9/9, build 6/6 (Linux CI)
Documents produced:
1. | P13-POLICY-RECONCILIATION-v3.md — corrected policy specification
2. | P13-BUSINESS-APPROVAL-TRACKING-REGISTER-v2.xlsx — this workbook
3. | P13-IMPLEMENTATION-READINESS-AND-PHASE-PLAN.md — phased plan (Phase 0–3)
4. | P13-POLICY-CONFLICT-AND-DEPENDENCY-REPORT.md — 6 contradictions, dependency graph
Attestation:
• | No repository files, code, migrations, tests, or configuration were modified.
• | No commits, pushes, deployments, or release authorizations were performed.
• | No provisional preference was interpreted as formal approval.
• | No approver identities, dates, or evidence were invented.
• | Baseline: branch develop, HEAD 8d60e36, clean working tree.