## Decision Register
Decision ID | Policy Area | Provisional Wording | Requester's Provisional Preference | Formal Approval Status | Required Approver Role | Actual Approver Name | Approval Date | Approval Evidence Reference | Outstanding Clarification | Dependencies | Implementation Impact | Release-Gate Impact | Notes & Next Action
D01 | Buyer Return Window | A return request must be raised within 14 days of the sub-order delivery timestamp (deliveredAt + 14 days). | Provisionally accepted by requester — formal business approval pending. | PENDING — NOT APPROVED | Head of Operations / COO (co: Customer Experience) | UNKNOWN | NOT PROVIDED | NOT PROVIDED | How does return eligibility interact with cancellations, partial deliveries, and exceptional cases (e.g. buyer never received)? | None — foundational window | Implemented in returns.service.ts (RETURN_WINDOW_DAYS constant). No code change required if 14 days approved. | BLOCKED — business approval required before release. | Lock §5.2. Existing code uses env-overridable RETURN_WINDOW_MS. Next action: business owner to approve 14-day value or specify alternative.
D02 | Merchant Response SLA | The merchant must respond to a return request within 72 hours of request creation. When the deadline passes, the request is escalated to an administrator and remains open. | Provisionally accepted by requester — formal business approval pending. | PENDING — NOT APPROVED | Head of Merchant Partnerships | UNKNOWN | NOT PROVIDED | NOT PROVIDED | What is the authoritative event and timestamp that starts the 72-hour clock? Is it return request creation, or a different trigger? | D03 (merchant timeout behavior), D11 (admin escalation SLA) | Currently stored as return_requests.expires_at. Current code auto-expires (REQUESTED→EXPIRED). If escalation policy approved, requires FSM amendment + worker redesign + migration 0059 CHECK constraint update. | BLOCKED — approval required. Material implementation change if escalation (not auto-expire) is confirmed. | Lock §5.8 BD-P13-EXCEPT-004. Next action: confirm 72h value and escalation behavior.
D03 | Merchant Timeout Behavior | When the merchant response deadline passes without action, the request is escalated to an administrator and remains open. Merchant non-response alone must not automatically approve, reject, or expire the request. | Provisionally accepted by requester — formal business approval pending. | PENDING — NOT APPROVED | Head of Merchant Partnerships (co: Head of Operations) | UNKNOWN | NOT PROVIDED | NOT PROVIDED | None — provisional policy is clear. Implementation requires FSM state ESCALATED + migration + worker redesign. | D02 (merchant response SLA), D11 (admin escalation SLA) | MATERIAL CHANGE: Add ESCALATED state to FSM, update migration 0059 CHECK constraint, redesign ReturnExpirationWorker to escalate (not expire), add admin escalated-queue UI. New outbox event return.escalated. | BLOCKED — approval required. This is a material FSM and worker behavior change from current implementation. | Conflict C-01 in reconciliation report. Current code: REQUESTED→EXPIRED (terminal). Proposed: REQUESTED→ESCALATED (non-terminal). Next action: business approval of escalation policy.
D04 | Commission — Merchant-Responsible | Reverse the commission attributable to the net value of goods refunded for confirmed merchant-responsible returns. Commission reversal must use authoritative checkout-time commission snapshots. | Provisionally accepted by requester — formal business approval pending. | PENDING — NOT APPROVED | Finance Lead / CFO | UNKNOWN | NOT PROVIDED | NOT PROVIDED | What is the approved deterministic allocation method when commission snapshots exist only at order level (not per-item)? | D06, D07 (consistent treatment across responsibility categories) | MATERIAL CHANGE: Current code retains commission for all cases. Requires refund calculation logic extension, settlement adjustment path for commission reversal, new responsibility_category field on return_requests. VAT-exclusive calculation only. | BLOCKED — approval required. Material financial logic change. | Conflict C-02. Lock §7.2 BD-P13-COMM-001 currently says "Commission is NOT adjusted." Next action: Finance to approve responsibility-dependent commission reversal.
D05 | Commission — Buyer Remorse | Retain the original commission for buyer-remorse (CUSTOMER_REQUEST) returns. No commission reversal. | Provisionally accepted by requester — formal business approval pending. | PENDING — NOT APPROVED | Finance Lead / CFO | UNKNOWN | NOT PROVIDED | NOT PROVIDED | None — provisional policy is clear. Buyer-remorse returns do not reverse commission. | D04, D06, D07 (consistent treatment across responsibility categories) | No change from current behavior (commission retained for all). Must be implemented as an explicit branch in responsibility-dependent commission logic. | BLOCKED — approval required for consistency with D04/D06/D07. | Constraint §5.3: buyer-remorse returns must not reverse commission. Next action: Finance to confirm.
D06 | Commission — Platform-Responsible | Reverse the commission attributable to the net value of goods refunded for confirmed platform-responsible returns (same treatment as merchant-responsible). | Provisionally accepted by requester — formal business approval pending. | PENDING — NOT APPROVED | Finance Lead / CFO | UNKNOWN | NOT PROVIDED | NOT PROVIDED | None — resolved in provisional policy. Same treatment as merchant-responsible. | D04, D05, D07 (consistent treatment across responsibility categories) | Same implementation as D04 — responsibility-dependent commission reversal logic. | BLOCKED — approval required. | Previously UNRESOLVED, now resolved in provisional policy. Next action: Finance to formally approve.
D07 | Commission — Carrier Damage | Reverse the commission attributable to the net value of goods refunded for confirmed carrier-damage returns (same treatment as merchant-responsible). Carrier recovery is pursued separately and is not implemented in P13. | Provisionally accepted by requester — formal business approval pending. | PENDING — NOT APPROVED | Finance Lead / CFO | UNKNOWN | NOT PROVIDED | NOT PROVIDED | None — resolved in provisional policy. Carrier recovery is a separate workflow. | D04, D05, D06, D10 (carrier-damage delivery fee) | Same implementation as D04/D06 — responsibility-dependent commission reversal logic. | BLOCKED — approval required. | Previously UNRESOLVED, now resolved in provisional policy. Next action: Finance to formally approve.
D08 | Delivery Fee — Full Sub-Order Baseline | The original delivery fee is refunded only for a full-sub-order return (all items, full quantity). Partial returns refund goods + proportional VAT only. | Provisionally accepted by requester — formal business approval pending. | PENDING — NOT APPROVED | Finance Lead (co: Head of Operations) | UNKNOWN | NOT PROVIDED | NOT PROVIDED | What is the delivery-fee allocation and refund treatment for mixed-item and partial-sub-order returns when an exception is approved? | D09, D10 (delivery-fee exceptions) | Already implemented in P13 (AC-P13-006 verified 10/10 in p13-financial-dispute.postgres.spec.ts). No code change if baseline approved as-is. | BLOCKED — approval required for baseline. | Lock §7.3 BD-P13-FEE-001/002/003. Verified by browser E2E B03 (partial return excluded delivery fee). Next action: Finance to approve baseline.
D09 | Delivery Fee — Admin Exception | Permit an administrator-authorized delivery-fee exception for confirmed merchant-responsible or platform-responsible partial returns, with the reason recorded in the audit trail. | Provisionally accepted by requester — formal business approval pending. | PENDING — NOT APPROVED | Finance Lead (co: Head of Operations) | UNKNOWN | NOT PROVIDED | NOT PROVIDED | What approval and audit evidence is required for delivery-fee exceptions? What UI workflow is needed? | D08 (baseline), D03 (escalation path for admin review) | Requires admin UI override path for delivery-fee refund on partial returns. New audit trail field for exception reason. Delivery-fee refund calculation extension. | BLOCKED — approval required. | Conflict C-03. Current lock says delivery fee refunded ONLY for full sub-order. Next action: Finance + Ops to approve exception path.
D10 | Delivery Fee — Carrier Damage | For confirmed carrier damage, refund the buyer's original delivery fee when damage materially compromises delivery of the order as a whole. Send limited-impact partial cases to administrator review. Pursue carrier recovery separately where possible. | Provisionally accepted by requester — formal business approval pending. | PENDING — NOT APPROVED | Finance Lead (co: Head of Operations) | UNKNOWN | NOT PROVIDED | NOT PROVIDED | Define "materially compromises delivery of the order as a whole" vs. "limited-impact partial cases." What are the eligibility thresholds? | D07 (carrier-damage commission), D08 (baseline), D09 (exception path) | Requires carrier-damage classification logic, delivery-fee refund path for carrier damage, admin review UI for partial cases. Carrier recovery is NOT implemented. | BLOCKED — approval required. | Previously UNRESOLVED, now resolved in provisional policy. Carrier recovery is a separate workflow not part of P13. Next action: Finance to approve + define materiality threshold.
D11 | Administrator Escalation SLA | The provisional administrator resolution target is 3 business days from escalation. The business calendar, timezone, holiday handling, and overdue-escalation process remain to be specified and approved. | Provisionally accepted by requester — formal business approval pending. | PENDING — NOT APPROVED | Head of Operations / COO | UNKNOWN | NOT PROVIDED | NOT PROVIDED | Define: business day, business hours, time zone, weekends, public holidays for the 3-business-day target. What happens when SLA is exceeded? Overdue-escalation process? | D02 (merchant response SLA), D03 (escalation behavior) | Requires business-calendar configuration, SLA tracking, overdue-alert mechanism. Not a core FSM change but an operational monitoring addition. | BLOCKED — approval required. Calendar/timezone definition needed before implementation. | Previously UNRESOLVED, now resolved in provisional policy (3 business days). Calendar details still TBD. Next action: Ops to define business calendar rules.
D12 | Settlement Recovery | Recover settlement amounts through manual Finance/administrator adjustments. No automated clawback. Post-finalization financial changes use auditable refund and settlement-adjustment records; finalized order financial snapshots remain immutable. | Provisionally accepted by requester — formal business approval pending. | PENDING — NOT APPROVED | Financial Controller | UNKNOWN | NOT PROVIDED | NOT PROVIDED | What Finance reconciliation and authorization requirements apply to manual settlement adjustments? Who can authorize an adjustment? | None — standalone financial process decision | Already implemented in P13 (AC-P13-013 PAID→ADJUSTMENT, AC-P13-014 PENDING/CALCULATED in-place). Verified by p13-financial-dispute.postgres.spec.ts. No code change if approved as-is. | BLOCKED — approval required. | Lock §7.1. Constraint §5.5: immutable finalized order financial breakdowns. Constraint §5.7: settlement recovery is manual. Next action: Financial Controller to approve.
D13 | Voucher Returns | Require administrator review for every voucher-related return. Voucher refunds are not auto-issued on merchant inspection alone. | Provisionally accepted by requester — formal business approval pending. | PENDING — NOT APPROVED | Finance Lead (co: Risk / Fraud) | UNKNOWN | NOT PROVIDED | NOT PROVIDED | What are the permitted outcomes after administrator review (cash, voucher, store credit, reject)? What are the financial consequences of each? Is there a value threshold? | None — standalone fraud-control decision | Admin oversight gating partially implemented (AC-P13-005/AC-P13-023 403 + denied UI). May need explicit voucher-review workflow in admin UI. | BLOCKED — approval required. | Lock §7.4. Constraint §5.6: voucher-related returns require admin review. Next action: Finance + Risk to approve + define permitted outcomes.
D14 | Deployment Target | Target a limited single-process pilot, subject to all operational and release gates. Multi-instance production remains blocked until a durable or leader-coordinated scheduler is implemented, tested, and independently verified. | Provisionally accepted by requester — formal business approval pending. | PENDING — NOT APPROVED | CTO / Head of Engineering (co: Operations) | UNKNOWN | NOT PROVIDED | NOT PROVIDED | What is the exact pilot environment, scope, start criteria, and success criteria? When does the pilot transition to production? | D15 (operational controls) | No code change for pilot selection. Multi-instance production blocked until durable scheduler implemented. | BLOCKED — deployment target must be explicitly selected before release. | Sign-off register §2. Constraint §5.8: in-process worker not approved for unrestricted multi-instance. Next action: CTO to select pilot target.
D15 | Pilot Operational Controls | Use the single-process pilot deployment model, with exactly one worker-enabled API instance and the four specified operational controls: (1) alert on repeated worker polling errors, (2) monitor REQUESTED rows overdue by >10 min, (3) designate exactly one worker-enabled API instance, (4) monitor worker startup and activity. | Provisionally accepted by requester — formal business approval pending. | PENDING — NOT APPROVED | CTO / Head of Engineering (co: Platform Ops / SRE) | UNKNOWN | NOT PROVIDED | NOT PROVIDED | Who are the named operational owners, alert recipients, monitoring thresholds, and pilot rollback responsibility? | D14 (deployment target) | Requires operational runbook, alerting configuration, monitoring dashboards. No code change to the worker itself. | BLOCKED — all four controls must be assigned and confirmed before pilot release. | Sign-off register §2 Option A. Constraint §5.9: all four operational controls required. Next action: Ops/SRE to accept controls and name owners.

## Open Questions
Question ID | Category | Question | Responsible Role | Decision Needed | Impact if Unresolved | Related Decisions | Status
OQ-01 | SLA Calendar | What is the definition of a business day, business hours, time zone, weekends, and public holidays for the administrator's 3-business-day escalation target? | Head of Operations / COO | Define business calendar rules: which days are business days, what hours, which timezone, which holidays are observed. | Cannot implement SLA tracking or overdue-alert mechanism without calendar definition. | D11 | OPEN
OQ-02 | SLA Triggers | What is the authoritative event and timestamp that starts each applicable SLA (merchant 72h clock, administrator 3-business-day clock)? | Head of Operations / COO | Confirm: merchant clock starts at return request creation timestamp. Admin clock starts at escalation event timestamp. Or specify alternatives. | Incorrect trigger definition causes premature or delayed SLA measurement. | D02, D11 | OPEN
OQ-03 | Return Eligibility | How does the 14-day return eligibility window interact with delivery timestamps, cancellations, partial deliveries, and exceptional cases (e.g. buyer never received, carrier-damaged delivery)? | Head of Operations / COO (co: Customer Experience) | Define: does the clock start at deliveredAt, at actual receipt, at last partial delivery? What about cancelled orders, undeliverable orders, carrier-damaged deliveries? | Ambiguous eligibility rules cause incorrect return request acceptance/rejection. | D01 | OPEN
OQ-04 | Commission Allocation | What is the approved deterministic allocation method when commission snapshots exist only at order level (not per-item)? | Finance Lead / CFO | Define: proportional allocation by item value ratio, equal split, or other method. Must be deterministic and auditable. | Without a defined method, commission reversal calculations are ambiguous for multi-item orders. | D04, D06, D07 | OPEN
OQ-05 | Delivery-Fee Allocation | What is the delivery-fee allocation and refund treatment for mixed-item and partial-sub-order returns when an admin exception is approved? | Finance Lead (co: Head of Operations) | Define: is the full delivery fee refunded on exception, or a proportional share? How is "proportional" calculated? | Ambiguous delivery-fee allocation causes incorrect refund amounts. | D08, D09, D10 | OPEN
OQ-06 | Delivery-Fee Exception Audit | What approval and audit evidence is required for delivery-fee exceptions? What UI workflow and authorization level is needed? | Finance Lead (co: Risk / Fraud) | Define: who can approve a delivery-fee exception, what reason codes are valid, what audit trail is required. | Without defined audit requirements, exception approvals lack governance. | D09, D10 | OPEN
OQ-07 | Settlement Adjustment Authorization | What Finance reconciliation and authorization requirements apply to manual settlement adjustments? Who can authorize an adjustment, and what review cycle is required? | Financial Controller | Define: authorization levels for adjustment amounts, reconciliation frequency, review sign-off process. | Without defined authorization, manual adjustments lack financial governance. | D12 | OPEN
OQ-08 | Voucher Handling | What are the permitted outcomes after administrator review of a voucher-related return? What are the financial consequences of each outcome? | Finance Lead (co: Risk / Fraud) | Define: permitted outcomes (cash refund, voucher reissue, store credit, reject), financial treatment of each, value thresholds if any. | Without defined outcomes, admin reviewers have no policy guidance for voucher cases. | D13 | OPEN
OQ-09 | Pilot Operations | Who are the named operational owners, alert recipients, monitoring thresholds, and pilot rollback responsibility for the four operational controls? | CTO / Head of Engineering (co: Platform Ops / SRE) | Name: alert recipients for each control, escalation thresholds, rollback decision authority, pilot duration and success criteria. | Without named owners, operational controls are unowned and unenforced. | D14, D15 | OPEN
OQ-10 | Pilot Scope | What is the exact pilot environment, scope, start criteria, and success criteria for the limited single-process pilot? | CTO / Head of Engineering (co: Head of Operations) | Define: which environment (staging? production subset?), which merchants/buyers, start conditions, success metrics, exit criteria. | Without defined scope, the pilot has no measurable success/failure criteria. | D14, D15 | OPEN
OQ-11 | Carrier Damage Materiality | What defines "materially compromises delivery of the order as a whole" vs. "limited-impact partial cases" for carrier-damage delivery-fee treatment? | Finance Lead (co: Head of Operations) | Define: materiality threshold (e.g. >50% of items damaged, all items damaged, delivery unusable). What constitutes limited-impact? | Without a materiality definition, carrier-damage delivery-fee exceptions are arbitrary. | D10 | OPEN
OQ-12 | Carrier Recovery | What is the carrier recovery process and eligibility? Who initiates, what evidence is required, and what is the recovery timeline? | Head of Operations / COO (co: Finance) | Define: carrier recovery workflow, evidence requirements, timeline, write-off threshold. Note: carrier recovery is NOT implemented in P13. | Without a defined process, carrier recovery is ad hoc and unauditable. | D07, D10 | OPEN — NOT IN P13 SCOPE

## Release Gates
Gate ID | Gate Name | Description | Status | Blocking Decisions | Evidence Available | Action Required
G-01 | Formal Business Approval | All 15 policy decisions (D01–D15) formally approved by designated approvers with attributable evidence. | BLOCKED | D01–D15 (all) | 0 of 15 decisions approved. No approver names, dates, or evidence provided. | Business owners must approve each decision with name, role, date, and rationale recorded in the Decision Register.
G-02 | Policy Ambiguity Resolution | All 12 open questions (OQ-01–OQ-12) resolved with definitive answers. | BLOCKED | OQ-01–OQ-12 (all) | 12 open questions identified. 0 resolved. | Responsible roles must provide definitive answers to each open question.
G-03 | Technical Implementation | FSM amendment (ESCALATED state), responsibility-dependent commission, delivery-fee exceptions, escalation worker, and admin UI implemented and verified. | BLOCKED | D03, D04, D06, D07, D09, D10, D11 | Current code implements auto-expire (not escalate) and uniform commission retention. Implementation not started for proposed changes. | Implementation authorized only AFTER business approval of D03, D04–D07, D09, D10, D11. Then: implement, test, verify.
G-04 | Commission & Settlement Correctness | Commission reversal calculations verified against immutable checkout-time snapshots. Settlement adjustments verified for all responsibility categories. Cumulative partial-return rounding verified. | BLOCKED | D04, D05, D06, D07, D12 | Current tests verify commission retention for all cases. Responsibility-dependent tests not yet written. | After implementation: write and pass integration tests for each responsibility category's commission and settlement treatment.
G-05 | Worker Scheduling & Deployment Topology | Worker scheduling verified for the selected deployment target. Single-process pilot: exactly one worker-enabled instance. Multi-instance: durable scheduler implemented and verified. | BLOCKED | D14, D15 | Current worker registers on every API replica with no enable/disable flag. Pilot topology not yet confirmed. | After D14/D15 approval: configure pilot topology, verify single-instance constraint, or implement durable scheduler for multi-instance.
G-06 | Pilot Operational Readiness | All four operational controls assigned to named owners, alerting configured, monitoring dashboards active, rollback plan documented. | BLOCKED | D15, OQ-09, OQ-10 | 0 of 4 controls assigned. No named owners, no alerting configured. | After D15 approval: assign owners, configure alerts, build dashboards, document rollback plan.
G-07 | Deployment Target Sign-Off | Deployment target explicitly selected (pilot or multi-instance). If pilot, all controls accepted. If multi-instance, durable scheduler verified. | BLOCKED | D14 | Target not selected. Neither option confirmed. | CTO / Head of Engineering must explicitly select deployment target and confirm associated conditions.
G-08 | Explicit Release Authorization | Authorized person grants explicit release authorization for commit/push/deploy. Not inferred from technical verification or provisional preferences. | BLOCKED | G-01 through G-07 (all must pass first) | No release authorization granted. Gate: PASS WITH CONDITIONS — RELEASE AUTHORIZATION PENDING. | After all other gates pass: authorized person must explicitly grant release authorization.
G-09 | Regression & Build Verification | Full regression suite passes (3098/3098 baseline). Focused P13 suites pass (162/162 baseline). Production build passes (typecheck 9/9, build 6/6). | PASS (pre-implementation) | None — prerequisite for post-implementation re-verification | Linux CI: 3098/3098 full, 162/162 P13, typecheck 9/9, build 6/6. Windows: identical results. | Re-verify after implementation changes. Current evidence is pre-implementation baseline.
G-10 | P12 Regression Preservation | All P1–P12 existing tests continue to pass. No regressions introduced by P13 implementation changes. | PASS (pre-implementation) | None — prerequisite for post-implementation re-verification | Full regression 3098/3098 includes all P1–P12 tests. 0 failures. | Re-verify after implementation. Constraint §5.10: P12 regression coverage must be preserved.

## Approval Guide
Category | Decisions | Approver Role | Approval Sequence | Rationale | Dependencies | Open Questions
Return Window & Eligibility | D01 | Head of Operations / COO (co: Customer Experience) | 1st | Foundational window — all other return policies depend on a defined eligibility period. Must be approved first. | None | OQ-03
Merchant Response & Escalation | D02, D03, D11 | Head of Merchant Partnerships (D02, D03) + Head of Operations / COO (D11) | 2nd | Merchant SLA and timeout behavior are coupled (D02 defines the clock, D03 defines what happens when it expires). D11 defines the admin resolution target. Must be approved before FSM/worker implementation. | D01 (eligibility window must be defined) | OQ-01, OQ-02
Commission Treatment | D04, D05, D06, D07 | Finance Lead / CFO | 3rd | All four commission decisions form a single responsibility-dependent policy. Must be approved as a coherent set — approving some without others creates inconsistent financial treatment. | D02, D03 (responsibility classification depends on escalation path) | OQ-04
Delivery-Fee Treatment | D08, D09, D10 | Finance Lead (co: Head of Operations) | 3rd (parallel with commission) | Delivery-fee baseline (D08), exception path (D09), and carrier-damage treatment (D10) form a coherent set. Can be approved in parallel with commission decisions. | D08 must be approved before D09/D10 (exceptions reference the baseline) | OQ-05, OQ-06, OQ-11
Settlement & Voucher Policy | D12, D13 | Financial Controller (D12) + Finance Lead / Risk (D13) | 4th | Settlement recovery (D12) and voucher review (D13) are operational financial policies. Can be approved independently of commission/delivery-fee decisions. | None — standalone financial process decisions | OQ-07, OQ-08
Deployment & Operations | D14, D15 | CTO / Head of Engineering (co: Platform Ops / SRE) | 5th | Deployment target (D14) and operational controls (D15) must be approved after all policy decisions are settled, since the pilot scope depends on the approved policy set. | D01–D13 should be approved first (pilot scope depends on approved policies) | OQ-09, OQ-10
EXECUTIVE SUMMARY
Total decisions: | 15 (D01–D15)
Approved: | 0 of 15
Pending approval: | 15 of 15
Open questions: | 12 (OQ-01–OQ-12)
Release gates: | 8 BLOCKED, 2 PASS (pre-implementation)
Primary blockers:
1. | No business decision has been formally approved. All 15 remain PENDING.
2. | 12 open questions require answers before implementation can be scoped.
3. | No deployment target has been selected.
4. | No release authorization has been granted.
5. | Material implementation changes (FSM escalation, responsibility-dependent commission) are not started and cannot start without approval.
Current gate: | PASS WITH CONDITIONS — RELEASE AUTHORIZATION PENDING
Technical verification: | COMPLETE — full regression 3098/3098, P13 suites 162/162, typecheck 9/9, build 6/6 (Linux CI verified)
Missing approval evidence: | ALL decisions — no approver names, dates, or evidence provided for any decision
Attestation:
• | No repository files, code, migrations, tests, configuration, or workflows were changed by this task.
• | No commits, pushes, merges, deployments, or release authorizations were performed.
• | No provisional preference was interpreted as formal business approval.
• | No approver identities, approval dates, or meeting minutes were invented.
• | Baseline preserved: branch develop, HEAD 8d60e36, clean working tree.
DOCUMENTS INSPECTED
P13-BUSINESS-SIGNOFF-REGISTER.md (114 lines)
P13-PROVISIONAL-POLICY-RECONCILIATION.md (469 lines)
P13-RELEASE-FOLLOW-UPS.md (32 lines)
SCS-CATALOG-PRODUCT-MANAGEMENT-PHASE-10-P13-BUSINESS-SIGNOFF-AND-RELEASE-AUTHORIZATION-REPORT.md (167 lines)
SCS-CATALOG-PRODUCT-MANAGEMENT-PHASE-10-P13-BUSINESS-RULES-ARCHITECTURE-LOCK.md (927 lines)
SCS-CATALOG-PRODUCT-MANAGEMENT-PHASE-10-P13-LINUX-CI-BUILD-VERIFICATION.md (115 lines)
SCS-CATALOG-PRODUCT-MANAGEMENT-PHASE-10-P13-LINUX-REGRESSION-VERIFICATION.md (167 lines)
Source: apps/api/src/modules/returns/returns.service.ts, return-expiration.worker.ts, returns.schema.ts